## Gantt Chart (overview)
SNOWCAT Spring 2018 Timeline
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43125 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Project duration (spring 2018) | 2018-01-25 | 2018-04-26 | 91 | 9.1 | 81.9 | 10%
SOLIDWORKS modeling and design | 2018-01-25 | 2018-02-14 | 20 | 16 | 4 | 80%
Electronics Power Testing | 2018-02-06 | 2018-02-14 | 8 | 0 | 8 | 0%
PCB design | 2018-01-25 | 2018-02-14 | 20 | 2 | 18 | 10%
Software and code development | 2018-01-25 | 2018-03-01 | 35 | 3.5 | 31.5 | 10%
Ordering parts | 2018-02-01 | 2018-02-22 | 21 | 16.8 | 4.2 | 80%
Manufacturing Readiness Review | 2018-02-19 | 2018-02-20 | 1 | 0 | 1 | 0%
Machining | 2018-02-20 | 2018-03-14 | 22 | 0 | 22 | 0%
Assembly | 2018-03-14 | 2018-04-01 | 18 | 0 | 18 | 0%
Prototype and test electronics subsystems | 2018-02-14 | 2018-03-20 | 34 | 0 | 34 | 0%
Structure subsystem testing | 2018-03-01 | 2018-03-20 | 19 | 0 | 19 | 0%
Test Readiness Review | 2018-03-19 | 2018-03-20 | 1 | 0 | 1 | 0%
Spring Break | 2018-03-24 | 2018-04-01 | 8 | 0 | 8 | 0%
Full system testing | 2018-04-01 | 2018-04-23 | 22 | 0 | 22 | 0%
Documentation (user manual for assembly, software and data analysis) | 2018-03-24 | 2018-04-26 | 33 | 0 | 33 | 0%
Deployment Readiness Review | 2018-04-20 | 2018-04-26 | 6 | 0 | 6 | 0%
0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## SYS RAIL (detailed)
Action Item ID | Action Item Description | Status open,open(late),closed,escalated,cancelled | Priority high,med,low | Function Role classification | Stakeholder ONE Requesters name | Owner ONE responsible party | Open Date | Initial Due Date | Actual Due Date | Status follow-up Initials/Date: text Initials/Date: text | Escalated To Initials/Date: text
1 | Finalize Requirements | open | high | Management | Haysley | Butler | 2018-01-25 | 2018-02-01 | 2018-02-01
2 | Make timeline | open | high | Management | Haysley | Haysley | 2018-01-25 | 2018-02-01 | 2018-02-01
3 | Make budget breakdown | open | high | Management | Haysley | Haysley | 2018-01-25 | 2018-02-01 | 2018-02-01
4 |  | open
5 |  | open
6 |  | open
7 |  | open
8 |  | open |  | Design
9 |  | cancelled | med | Analysis
10 |  | closed | low | Testing

## EPS RAIL (detailed)
Action Item ID | Action Item Description | Status open,open(late),closed,escalated,cancelled | Priority high,med,low | Function Role classification | Stakeholder ONE Requesters name | Owner ONE responsible party | Open Date | Initial Due Date | Actual Due Date | Status follow-up Initials/Date: text Initials/Date: text | Escalated To Initials/Date: text
1 | Finalize Requirements | open | high | Management | Haysley | Lyke | 2018-01-25 | 2018-02-01 | 2018-02-01
2 | PCB design | open | high | Design | Lyke | Lyke/Hadjis | 2018-01-26 | 2018-02-14 | 2018-02-14
3 | Software and code development | open | high | Design | Lyke | Lyke/Hadjis | 2018-01-27 | 2018-02-21 | 2018-02-21
4 |  | open
5 |  | open
6 |  | open
7 |  | open
8 |  | open |  | Design
9 |  | cancelled | med | Analysis
10 |  | closed | low | Testing

## STR RAIL (detailed)
Action Item ID | Action Item Description | Status open,open(late),closed,escalated,cancelled | Priority high,med,low | Function Role classification | Stakeholder ONE Requesters name | Owner ONE responsible party | Open Date | Initial Due Date | Actual Due Date | Status follow-up Initials/Date: text Initials/Date: text | Escalated To Initials/Date: text
1 | Finalize Requirements | closed | high | Management | Haysley | Palma | 2018-01-25 | 2018-02-01 | 2018-02-01
2 | Solidworks modeling | open | high | Design | Palma | Doster | 2018-01-25 | 2018-02-07 | 2018-02-14
3 | Solidworks drawings | open | high | Design | Palma | Doster | 2018-01-25 | 2018-02-14 | 2018-02-21
4 | Manufacturing | open | med | Design | Palma | Doster | 2018-02-14 | 2018-03-24 | 2018-03-24
5 | Sourcing and ordering parts | open | med | Design | Palma | Doster | 2018-02-14 | 2018-02-28 | 2018-02-28
6 | Assembly | open | med | Design | Palma | Doster | 2018-03-24 | 2018-04-07 | 2018-04-07
7 |  | open
8 |  | open
9 |  | cancelled | med | Analysis
10 |  | closed | low | Testing
Updated 2/5/2018 11 AM by Palma